## Sheet1
Risk Register for iVolunteer Social Network
Prepared by: |  | SonNT |  | Date: | 2016-05-16
No | Risk | Description | Category | Root Cause | Triggers | Avoidance plan | Contigency plan | Fallback plan
1 | Conflict opinion between members |  | People | Different opinions | A problem has many perspectives, solutions | Describle problem as detailed as possible | Meeting to solve conflict, voting | Expell member from team
2 | Unexpected accidents |  | People |  | Sickness, accidents | Raational plan, members should take care of self's health | Accept delay or other members share tasks | Replan project
3 | Members lack of practical experience |  | People | Members are all students | Lack of mindset, knowledge about technique and management |  | Trainning mindset, study technique, have Supervisor
4 | Requirement change |  | Process | SRS does not meet user requirement | Customer change requirement or some of requirements can be developed | Carefully analyze user requirement, know exactly team potentials, review by PM or Supervisor | Team should have a meeting to analyze change and decide actions | Re-estimate and update project plan Update requirement
5 | Members do not meet dealine |  | Process | Members delay or have unexpected accidents | Have a deadline | Raational plan, penalty if not meet dealine | Team should have a meeting to analyze reasons | Other members share tasks
6 | Product does not meet requirement |  | Product | Members does not follow requirement or requirement did not include | Fail acceptance test | Carefully analyze user requirement | Team should have a meeting to analyze differents and decide actions | Delay release day and add missing required functions
7 | Delivery products late |  | Process | Some items in plan did not meet deadline or unexpected accidents | Deliver product after delivery date | All items in plan must meet or earlier than deadline in plan | Appology customers and decide nearest delivery date
8 | Infrastructure breakdown |  | Infrastructure |  | Laptops broken | Periodically check avaiability and maintain | Borrow or buy new laptop and repair broken one | Work overtime to cover remain tasks if wasn't able to meet deadline due to breakdown